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Second Progress Report:

A FAMILY-BASED REINDEER ECONOMY, AND

THE STATUS AND MANAGEMENT OF WILD REINDEER/CARIBOU POPULATIONS

Purpose of the project

This project is a follow-up of the “Sustainable Reindeer Husbandry” project presented at the Third Arctic Council Ministerial Meeting in Finland in October 2002 (Inari SAO-report, page 29). That project focused on reindeer husbandry in the circumpolar region.  This project expands the scope of inquiry in a number of areas. Instead of focusing exclusively on the herders, as the previous project did, it will examine the role of the whole family in reindeer husbandry. It will also study wild reindeer/caribou populations as well as the indigenous societies which hunt them. This will include a range of issues related to the traditional economies and ways of life of indigenous reindeer herders and hunters. 

The project focuses on two main challenges which were recognised in the recommendations of the International Steering Committee. These challenges are: 

a) development of a family-based reindeer/caribou economy, and 

b) co-existence between wild reindeer/caribou and domesticated reindeer around the circumpolar North

The project seeks to add to the base of scientific knowledge of the economics of family-based reindeer/caribou herding and hunting of wild reindeer/caribou as an animal/natural resource. 

Regarding family-based reindeer/caribou herding and hunting economies, the project will examine:

· the current social situation of herding and hunting families in the circumpolar North

· the current status of the role of women within family-based herding operations in herder societies. 

· the current potential for reviving a family-based reindeer herding and hunting economy for the indigenous peoples in different countries

· the potential for developing family-based value-added production in the industry

The project’s data collection process will make extensive use of socio-economic data which are already available in the different countries through public reports, annual reindeer herding reports, statistics and so forth. The latest data will be obtained from national reindeer herding authorities, herding organisations, and from field interviews with indigenous Arctic people. 

Regarding wild reindeer/caribou issues, the project will examine:

· the current situation regarding the growth and development of wild reindeer/caribou herds 

· wild reindeer/caribou population management practices in the individual countries and the problems associated with the co-existence of domesticated reindeer and caribou/wild reindeer on the same or adjacent rangelands

· external factors that affect wild reindeer/caribou populations 

· the economic and legal dimensions of wild reindeer/caribou resources for the indigenous families

Contribution to the Sustainable Development Framework Document and the forthcoming Action Plan on Sustainable Development

The focus of this project is on the development of an economically, socially and culturally sustainable family-based reindeer/caribou economy, which includes both the herders and the hunters among the indigenous populations.

Reindeer/caribou herding and hunting are Arctic livelihoods with specific cultural dimensions of fundamental importance to the indigenous people living there. Access to natural resources is therefore the key to sustainable human development in the Arctic. Other sustainable livelihoods are difficult to develop in these regions, so it is important to find solutions to the problems that have developed. If economic prosperity and social well-being are to be achieved, reindeer/caribou herding and hunting will have to be one of the economic and cultural mainstays of the future.  

Project timetable

There have been some changes in the time schedule: 

January – June 2003

· Contact national reindeer herding authorities and herding organisations in the participating countries and secure their co-operation

· April 7-8, Arctic Council Sustainable Development Working Group (SDWG) meeting in Iceland

· April 9-10, Arctic Council Senior Arctic Officials (SAO) meeting in Iceland 

· Field trips in Norway, Southern Sámi Areas (May) 

· Meeting with the Norwegian part of the project (May)

July – December 2003
· Fieldtrip to West-Chukota Autonomous Okrug (July/August)

· October 1, seminar in Moscow. Presentation of the Russian version of the Sustainable Reindeer Husbandry Report 

· October 2.-3., First International Steering Committee Meeting in Moscow

· October 22, Arctic Council SDWG-meeting in Iceland (Second Progress Report)

· October 23 – 24, Arctic Council SAO-meeting in Iceland 

· Preparation of a database of existing and relevant literature (October)

· Fieldtrips in Sweden, Norway and Finland (October and November)

· Fieldtrip in Nenets Autonomous Okrug (October/November) 

· November/December – start analysing the collected data

· Drafts of the chapters from each country (December)

January – June 2004
· Preparation of the chapters in the report (January - March)

· International workshop in Yakutsk, Russia – with presentation of the findings in the project (March)

· Second International Steering Committee Meeting, Yakutsk, Russia (March)

· April 1, first draft of the main report

· April 15, Draft of executive summary and recommendations 

· May 3, Arctic Council SDWG-meeting in Iceland (Third Progress Report)

· May 4-5, Arctic Council SAO-meeting in Iceland

· Third International Steering Committee Meeting, approval of the report and recommendations, Tromsø, Norway (June)

July – December 2004
· July: Final report 

· August 1, Submission of the report to the Arctic Council

· August 5, Printing of the report

· September 27-28, SAO-meeting in Akureyri, Iceland

· September 29-30, the Fourth Ministerial Meeting in Akureyri, Iceland, presentation of the report

· October-December – publication of scientific articles from the project

Based on the information that is obtained, the project will make recommendations on further action to the Arctic Council, to national authorities and to the industry itself. 

Date of approval, date of proposed finalisation

The final report, A Family-Based Reindeer Economy, and the Status and Management of Wild Reindeer/Caribou Populations, had its formal starting date January 2003, and will be presented at the Fourth Arctic Council Ministerial Meeting to be held in Iceland in September 2004. 

Leaders, participants

The members of the international steering committee are:

· Jan Tore Holvik, Senior Arctic Official, The Norwegian Ministry of Foreign Affairs (chair) 

· Tatjana S. Nikolajeva, Senior Consultant, The Russian Ministry of Agriculture (vice-chair)  

· Sigurd Svela, Adviser, The Norwegian Ministry of Agriculture                                 

· Johan-Klemet Kalstad, Senior Researcher, Nordic Sámi Institute, Kautokeino, Norway 

· Vasilij. A. Zabrodin, chairman of the co-ordination team for the north-western sector at the Academy of Agricultural Sciences, St. Petersburg  

· Dmitry Ottovitch Khorolya, President of the Reindeer Herders Union of Russia 
· Nina Hellström, Senior Officer, Finnish Ministry of Agriculture and Forestry

· Don Russell, Research Manager, Canadian Wildlife Service, Whitehorse 

· Gary Kofinas, Assistant Professor, University of Alaska, Fairbanks

· Per-Gustav Idivuoma, Chairman of the Sámi Reindeer Herding Organisation in Sweden

· Johan-Mathis Turi, President, Association of World Reindeer Herders
The project manager, Birgitte Ulvevadet, is based at the Centre for Sámi Studies, University of Tromsø, Norway, and is in charge of the day-to-day work. She is responsible for preparing the project report. Konstantin Klokov is the Russian co-ordinator and is based at the St.-Petersburg State University, Russia. He is responsible for the work in Russia. The project manager and project co-ordinator are both employed full-time on the project. 

Progress since last SDWG meeting

· First part of the project – The Sustainable Reindeer Husbandry Project

· The report from part one of the project, “Sustainable Reindeer Husbandry”, has been translated into Russian. 

· The Russian version of the Sustainable Reindeer Husbandry report was presented at a scientific seminar, hosted by the Royal Norwegian Embassy in Moscow. Researchers, public officials, organizations, media and other interested parties were invited to participate, cf. attachment 1 and 2. The successful seminar was organized by the Association of World Reindeer Herders, the Russian Ministry of Agriculture and the Royal Norwegian Embassy.   

· The Russian report has been distributed to universities, research institutions, public offices, organizations and others who have expressed an interest.

· The International Steering Committee

· On October 2. and 3., the project had the first meeting in the International Steering Committee. The Committee approved the project description and future work plans.

· Canada, Alaska and Sweden were invited to the International Steering Committee meeting in Moscow, October 1st and 2nd. New participants in the International Steering Committee are Research Manager, Don Russell from the Canadian Wildlife Service, Whitehorse, Assistant Professor, Gary Kofinas from the University of Alaska, Fairbanks, Chairman Per-Gustav Idivuoma from the Sámi Reindeer Herding Organisation in Sweden and Dmitry Ottovitch Khorolya, President of the Reindeer Herders Union of Russia. 
· We have had a very good response towards this project. As of now, Russia, Canada, Alaska, Finland, Sweden, Norway and the Association of World Reindeer Herders are represented in the International Steering Committee. 

· Experts in the project

· The project is working closely with reindeer herding organizations and/or native organizations in participating countries. The project finds it important to make good use of the valuable knowledge these organizations possess.

· Association of World Reindeer Herders have been engaged in the project to read texts, contribute with inputs, and help comparing the family-based reindeer husbandry in the different countries participating in the project. The project believes that this will increase the quality of the material. 

· Fieldtrips

· By October 1st the project has made fieldtrips to West-Chukota Autonomous Okrug in Russia and the Provinces of Hedemark, Sør-Trøndelag, Nord-Trøndelag, Nordland and Finnmark in Norway.

· During October, the project will make fieldtrips to Finland and Sweden. In Finland the project will visit the three reindeer husbandry areas in the Provinces of Lapland and Oulu; the Sami Reindeer Herding Area, the Special Reindeer Herding Area and the Reindeer Herding Area. In Sweden the fieldtrip will go to the tree main herding areas; Norrbotn, Västerbotn and Jämtland. 

· In November, the project will make fieldtrips to the Provinces of Troms and Finnmark in Norway. The project will also make fieldtrips in Russia; to Nenets Autonomous Okrug and/or the Komi Republic. 

· In Alaska and Canada data collection will be done between November/December 2003 and March 2004.

Main developments foreseen until next meeting

Cf. Project timetable.  

Capacity-building

The project seeks to:

· Increase the general knowledge of family-based reindeer herding and hunting economies of indigenous peoples, and strengthen its position on the Arctic Council’s agenda

· Enhance the general knowledge of the growth, development and management of wild reindeer/caribou herds, and draw the Arctic Council’s attention to this development

As indicated in the first report, the reindeer industry in general is facing serious problems that are the result of external pressures. Part of the focus will therefore be on developing an economically, socially and culturally sustainable family-based reindeer/caribou herding and hunting economy, with a stronger family based involvement. The scope of this project will thus encompass different groups of indigenous peoples.  

Further, the project will focus on traditional skills and knowledge and how they may be applied in new market-oriented industries. It will also look at the potential for developing family-based value-added production in the industry. 

The project will also focus on the growth and development of wild reindeer/caribou herds, population management practices in the individual countries and the problems associated with the co-existence of domesticated reindeer and wild reindeer/caribou. 

The insights thus obtained will be a valuable contribution to the exchange of knowledge that will take place as national representatives continue to work together in this field. 

The project will seek to build capacity through:  

1) a better understanding of central challenges a family-based reindeer/caribou economy and wild reindeer/caribou populations will face in the future, and what will be needed to meet these challenges. 

2) identifying problems and shortcomings in reindeer herding and hunting practices and economies, taking into account cultural variations and adaptations to local natural resource bases.

3) making recommendations on further action for national implementation and follow-up, and for further joint activities at the international level.
The gender perspective

The Sustainable Reindeer Husbandry report clearly indicates that most women are now employed outside the reindeer industry. The impact of modernisation has changed the role played by women in reindeer herding families. This project will therefore examine the current status of the role of women within family-based herding operations in herder societies.

Relation to the Arctic Human Development Report
As stated in the project proposal from the Arctic Human Development Report Task Force (AHDR), a comprehensive assessment of human conditions in the entire circumpolar region has never before been carried out. The traditional ways of life of the peoples in the region are inseparable from the reindeer industry and utilisation of wild reindeer/caribou as a resource. This project can therefore contribute with valuable information to the Arctic Human Development Report.  

We can be reached through:

Birgitte Ulvevadet

Project Manager

Centre for Sami Studies

University of Tromsø

9037 Tromsø, 

Norway

Phone: (+47) 77 64 64 66

GSM: 
(+47) 41 56 72 71

Fax: 
(+47) 77 67 66 72 

E-mail: birgitte.ulvevadet@sami.uit.no
Konstantin Klokov

Russian Co-ordinator

St.-Petersburg State University

41, Sredniy av.

St.-Petersburg 199004

Russia

Phone: (+7) 812 310 82 35

Fax: (+7) 812 328 05 72

E-mail: klokov@mailbox.alkor.ru
Further documentation can be found at our homepage:

http://uit.no/reindeer-husbandry
Attachments:

1. Programme for the Seminar in Moscow, 01 October 2003.

2. List of participants, Seminar in Moscow, 01 October 2003.

Sámi dutkamiid guovddáš / Centre for sami studies

University of Tromsø, N-9037 Tromsø, switchboard (+47) 77 64 40 00, fax (+47) 77 67 66 72

Birgitte Ulvevadet, project manager, direct line (+47) 77 64 64 66, e-mail: birgitte.ulvevadet@sami.uit.no
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